## Questions from enGen
yu | Raised by | Date | Response | Reponded by | Date | Status | Comments
Detailed tech diagram needed. Specifics required to build. | Joe Mostowy | 2025-09-03 |  |  |  |  | cloud resources related queries are under review from cloud engg team
Detailed security model needed. Map specifics to tech components where possible. | Joe Mostowy | 2025-09-03 | - IAM least-privilege service account. - TLS 1.2+ end-to-end (Cloud Run/Functions are HTTPS-only). - Secret Manager for processor IDs, tokens; no secrets in code. 1) Gemini API Key 2) Verexai Search Index I 3) DOcument AI- Laypout Parser ID - VPC + Serverless VPC Access, PSC to DocAI/Vertex/GCS (no public egress). No shared VPC 1) Document AI API 2) Vertesx ai API 3) Vertex Ai Search API 4) All cloud run and cloud functions - CMEK for GCS/Vertex Search; VPC-SC around data projects. 1)Cloud GCS 2) Bigquery |  |  |  | cloud resources related queries are under review from cloud engg team
Describe all uses of VPC networks, including dedicated VPCs, shared VPCs, and VPC peering. | Joe Mostowy | 2025-09-03 | Describe all uses of VPC networks, including dedicated VPCs, shared VPCs, and VPC peering. -One VPC per environment (e.g., dev, staging, prod) -Private Service Connect (PSC) endpoints for: aiplatform.googleapis.com us-documentai.googleapis.com storage.googleapis.com -Private DNS mapping to resolve PSC endpoints internally. ​​​​ |  |  |  | cloud resources related queries are under review from cloud engg team
​​​​​​​For resources that host data, specify expected clients and locations to assess required rules for VPC Service Control perimeters. | Joe Mostowy | 2025-09-03 | VPC - Cloud functions, run, storage where the files stored, processed, ready for indexing etc & PSC to DocAI APIs, Vertex AI search API,(no public egress). |  |  |  | cloud resources related queries are under review from cloud engg team
Describe any DR requirements and how they will be addressed. (backups, failover, etc) | Joe Mostowy | 2025-09-03 | - GCS + Vertex/DocAI. - Normalized JSON will be stored in bucket or folder for document processing with docai - Rebuild index by replaying normalized JSON in processed. - Traces will be stored in BQ for exceptions, corrupted chunks and the retry, reindexing, logging will be done
Specify any at-rest or in-transit encryption or encryption key handling requirements. | Joe Mostowy | 2025-09-03 | - Encryption in transit & at rest; key handling - In transit: HTTPS/TLS everywhere. - In Prod: Google-managed encryption (default) for GCS/Vertex/Logs. - Secrets: Secret Manager; rotate credentials every 90 days. - CMEK (Cloud KMS) for GCS buckets and Vertex Search (where supported); key rotation policy and access audit.
Specify any secrets management requirements. | Joe Mostowy | 2025-09-03 | - 90 days rotation for secrets
If PHI/PII (data level 3) are not in scope, what filtering or alerting mechanisms are in place to prevent them from entering the data streams? This is important, especially with various type of raw data being input (e.g. meeting minutes) | Joe Mostowy | 2025-09-03 | #NAME?
How much vector storage will be needed? (estimate. vectors and dimensions) | Joe Mostowy | 2025-09-03 | - Using Vertex AI Search (managed vectors). approx Size drivers: docs × avg_chunks × embedding_dim × 4 bytes. - Example: 5k docs × 20 chunks/doc × 768 dim × 4 ≈ 307 MB raw vectors (Search adds index overhead ≈ 1.5–2×). - Plan 1–2 GB for 5k docs, 20–40 GB for 100k docs (rule-of-thumb with overhead & metadata). Monitor actual via Vertex metrics.
What type of storage will be needed? (storage classes, scaling, latency, throughput, total sizing, etc) | Joe Mostowy | 2025-09-03 | #NAME?
How will the vector store be managed? | Joe Mostowy | 2025-09-03 | - MVP: Vertex AI Search (fully managed): automatic sharding, scaling, and index maintenance; push docs via API; monitor with Vertex metrics and quotas. - Prod: add index versioning (parallel data stores) for zero-downtime reindex; planned cutover + rollback.
Describe how relevant KPIs will be measured. | Joe Mostowy | 2025-09-03 | -Ingestion lag (upload → searchable), target < 15 min. -Indexing success rate (% of files indexed). -Parse errors (DocAI failure rate) -Draft and Final refinement workbook -Cost per 1000 docs (DocAI + Search calls).
Describe how the KPIs will be delivered and monitored. | Joe Mostowy | 2025-09-03 | Dashboards: Cloud Monitoring + custome UI (BQ data). Alerts: Ingestion lag > 15 min Indexing error rate > 2% Vertex Search indexing failures Weekly KPI snapshot auto-emailed (optional).
What cloud resources, if any, will be created through automation. Describe any automation triggers where needed. | Joe Mostowy | 2025-09-03 | -Cloud Run services/jobs, Functions, IAM bindings, log sinks, and Scheduler are deployed via Cloud Build to Artifact Registry → gcloud/Terraform. -Buckets typically provisioned by Terraform (naming/lifecycle consistent). -DocAI processor can be pre-created manually or via gcloud; access is automated (IAM). -Vertex Search data store preferably via Terraform (or one-time CLI), ongoing document upserts automated in pipeline.
Are the AI agents developed for use, accessed directly or are they being recreated? | Joe Mostowy | 2025-09-04 | #NAME?
Describe the specific LLM models that will be used. | Joe Mostowy | 2025-09-04 | -Gemini 2.5-flash
Explain the architecture from monitoring perspective? How we are ensuring continous monitoring of this capability | Rahul A | 2025-09-04 | -Dashboards: Cloud Monitoring + Looker Studio (BQ data). Alerts: Ingestion lag > 15 min Indexing error rate > 2% Vertex Search indexing failures Weekly KPI snapshot auto-emailed (optional).
What LLM model is planned to be used in this project and how model performace can be identified to be at the par of industry? | Rahul A | 2025-09-04 | Gemini 2.5 Flash and Google Cloud now offers out-of-the-box monitoring and alerting for Gemini and other foundation models directly from the Vertex AI dashboard Metrics Available: Request latency Token throughput Error rates (e.g., 429s, 5xx) Usage volume(tokens)
How is ethical testing is planned for the capability | Rahul A | 2025-09-04 | pre-ingestion check using DLP APIs to verify no PII information in storage ACL - Access control and leakage tests Safety and harmful content tests - Model armour Prompt injection tests Grounding, Auditabiity and explanability
Refer 9 and explain on data integrity and Privacy details. What actions are planned for it | Rahul A | 2025-09-04
Are there any Guardrails to ensure the LLM is not using inapproprite or unwanted subjects | Rahul A | 2025-09-04 | Model Armor for gaurdrails enforcing Zero Trust policies and sandboxing models during execution It restricts what models can access or execute—blocking unauthorized file reads, command execution, or network activity Model Armor uses KubeArmor to isolate AI workloads in secure containers. You can configure Model Armor templates to set thresholds for different types of content (e.g., HIGH confidence for hate speech, LOW for profanity).
How the audit trails and logs are maintained for all prompt and responses | Rahul A | 2025-09-04 | Custome tool to store the prompt template versions created by critic agent and outcomes using bigquery
Refer 2 and mention the about the access control | Rahul A | 2025-09-04

## Sheet1
Service accounts (3) and exact privileges 1) sa-deploy@<project>.iam.gserviceaccount.com — CI/CD only Used by Cloud Build/GitLab to build and deploy; no data access. roles/run.admin (If using Gen2 Functions) roles/cloudfunctions.admin roles/artifactregistry.writer roles/iam.serviceAccountUser on sa-ui and sa-pipeline roles/logging.viewer (deploy troubleshooting) --- 2) sa-ui@<project>.iam.gserviceaccount.com — UI runtime (Cloud Run) Serves the web app; may call your private APIs. roles/logging.logWriter roles/secretmanager.secretAccessor on specific UI secrets only (optional) If UI calls a private backend (file API, agent gateway): roles/run.invoker on that specific Cloud Run service No Storage, DocAI, Vertex, BigQuery, or indexing permissions. --- 3) sa-pipeline@<project>.iam.gserviceaccount.com — Ingestion/Extraction/Indexing & Agents (Cloud Run services/jobs / Gen2 Functions) Handles file ingest, calls Document AI, normalizes, indexes to Vertex AI Search, and invokes ADK/Agent Engine when needed. Logging: roles/logging.logWriter Secrets: roles/secretmanager.secretAccessor on named secrets (DocAI processor ID, Search data store ID, agent IDs, etc.) Cloud Storage (GCS): roles/storage.objectCreator on uploads bucket roles/storage.objectViewer on processed bucket (If parser writes normalized JSON) roles/storage.objectCreator on processed Document AI: roles/documentai.apiUser on the specific processor(s) Vertex AI Search / Discovery Engine (index & query): Indexing: roles/discoveryengine.editor on the target data store (documents write/update) Query (if this SA calls search/grounding): roles/discoveryengine.searchUser on that data store Vertex AI (ADK / Agent Engine / model inference): roles/aiplatform.user (invoke agents, tools, models, endpoints; run flows built with ADK/Agent Engine) BigQuery (only if you store KPIs/telemetry): roles/bigquery.dataEditor on the KPI dataset (Later, when you add private networking): roles/vpcaccess.user on the Serverless VPC Access connector --- Per-service coverage Service / Resource Covered by which SA Exact roles (scope) 1. Cloud Run – UI sa-ui logging.logWriter; (secretAccessor on specific secrets); run.invoker on backend if UI calls it 2. API Gateway / IAP (optional) Gateway/IAP SA (if used) run.invoker on targeted Cloud Run (no data roles) 3. Cloud Run – File ingestion API sa-pipeline storage.objectCreator on uploads; logging.logWriter; (secretAccessor if needed) 4. Cloud Run / Gen2 Function – Parser sa-pipeline documentai.apiUser (processor); storage.objectViewer (uploads); storage.objectCreator (processed); logging.logWriter 5. Cloud Run Job / Gen2 Function – Indexer sa-pipeline storage.objectViewer (processed); discoveryengine.editor (data store); logging.logWriter 6. Vertex AI Agent Builder / Agent Engine (ADK) sa-pipeline (or sa-ui only if UI calls agents directly—usually avoid) aiplatform.user; plus discoveryengine.searchUser if agent retrieves via Search 7. Vertex AI Search (Discovery Engine) sa-pipeline (write); sa-ui or sa-pipeline (read) discoveryengine.editor (write) & discoveryengine.searchUser (read) scoped to the data store 8. Document AI sa-pipeline documentai.apiUser on processor 9. Cloud Scheduler (optional) Scheduler SA run.invoker/cloudfunctions.invoker on target; or pubsub.publisher on topic 10. Eventarc / Pub/Sub sa-pipeline (publisher/subscriber as used) pubsub.publisher (topic) / pubsub.subscriber (subscription) 11. GCS buckets (uploads, processed, quarantine) sa-pipeline As above; UBLA on; lifecycle rules 12. BigQuery (KPIs) sa-pipeline (write), analysts (read) bigquery.dataEditor (dataset) / analysts: bigquery.jobUser + dataViewer 13. Artifact Registry sa-deploy (push), Cloud Run service agent (pull) artifactregistry.writer (CI); artifactregistry.reader (deploy/runtime) 14. Secret Manager sa-ui, sa-pipeline secretAccessor on named secrets only 15. Cloud Logging/Monitoring all runtimes logging.logWriter; viewers get logging.viewer, monitoring.viewer 16. VPC + PSC (future) runtimes vpcaccess.user on connector (network team manages VPC/PSC/DNS) 17. Cloud Armor (public front door) n/a WAF policy on LB—no SA roles 18. CMEK/KMS sa-pipeline (if accessing CMEK’d resources) cloudkms.cryptoKeyEncrypterDecrypter on the key --- Required APIs (one-time enablement) Cloud Run: run.googleapis.com (If Gen2 Functions) cloudfunctions.googleapis.com Cloud Storage: storage.googleapis.com Document AI: documentai.googleapis.com Vertex AI (Agents/Models): aiplatform.googleapis.com Vertex AI Search / Discovery Engine: included under aiplatform in most projects; enable via console if separate Artifact Registry: artifactregistry.googleapis.com Logging & Monitoring: logging.googleapis.com, monitoring.googleapis.com (If using triggers) eventarc.googleapis.com, cloudscheduler.googleapis.com (Later networking) compute.googleapis.com, vpcaccess.googleapis.com, servicenetworking.googleapis.com, dns.googleapis.com

## Questions from CT
Query | Raised by | Date | Response | Reponded by | Date | Status | Comments
1. columns expected in the final output and sheets ( Stake holders , Assumptions , Stakeholders , Dependencies)?
2. How many Input files and types of input files and is their template consistency and input source? |  |  | Input files are HLVS, Lean IA, Technical one pager, Vision diagrams, project specific excel spreadsheets, PDF's and meeting notes | Sooraj Mattappadan | 2025-09-05
3. for 60 projects how many man power utilizaion ? and how many weeks takes place to build 60 projects? |  |  | Question unclear
4. how many projects are generated weekely/monthly/yearly ? |  |  | I belive Subra already answered this
5. LLM agents might vary depending on the number of datapoints to be extracted in each sheet
6. Data security ( encryption , Processing)
7 . Latency can be calculated based on implementation?
8. Batch processings / realtime ? utilization of realtime generated data in downstreampipeline or anyother approach ?
9.Document Volume(HLVS,LEAN IA, POR, Capability Placemat)
10.Manpower utilizing for the generation ?
11. Some of the project folder like mavro the HLVS file is not opening |  |  | Please provide a list of HLVS thats not opening, we will try to re-upload | Sooraj Mattappadan | 2025-09-05
12.Some projects folder does not have ppts is there any specific reason |  |  | Teams are still trying to find the documents. Please refer to inventory spreadsheet to see which folders has which documents available | Sooraj Mattappadan | 2025-09-05
13. PEX project file contain the business requirement file which is docx but other folder dont have that |  |  | SOme projects may have docx doc for requirements. This may be the requirements from external sources like BCBS association, clients etc.. But there will always be an enGen powerpoint/excel requirements document | Sooraj Mattappadan | 2025-09-05
14. Project medigap 2026 Annual Imperative lean ia file contain the flow dia. what is the purpose of that |  |  | ITs conceptual/solution diagram. Model should be able to interpret and extract informayion from flows | Sooraj Mattappadan | 2025-09-05
15. Does the contend ppt from the project folder having same information as like leanIA and HLVS? |  |  | No In our B&E process. HLVS/lean IA are the input to requirement phase and PPT is the output | Sooraj Mattappadan | 2025-09-05
16. HLVS file from HI100638- Improvement to member flagging system project folder have different template format, how many other files have different template and what is purpose |  |  | enGen always uses standard template. The changes may be very slight. We can review it in our next meeting | Sooraj Mattappadan | 2025-09-05
17. What is the the file purpose: Final_20240812_self_funded_open_access_network project folder
18. Files starting with $ are not opening
19. Auto nation Surgery plus and Carrum Health project have LEAN IA file in excel format and reular LEAN IA in docx format , do we have to consider the excel file?
20.Could you please clarify whether "WY Risk Adjustment 2025" (listed in the project list) and "WY Risk Adjustment 2023" (found in the project folder) refer to the same project or two separate ones?
21.In some folders,a screenshot of an email included. what purpose it serves?(Project:PA Act 146 Appeals Codes)
22.For the same project, there are two PowerPoint files: Req Final and RFinal, what the difference is between these two versions? Project: 1003661_Federal Markets Sales Enablement (CRM)
23.In some folders, I noticed a screenshot of an email included. Could you please clarify what that’s about or what purpose it serves?(Project:PA Act 146 Appeals Codes)
24.Why are several project folders placed under the "POC" subfolder in the project folder?